## Sheet1
Milestone 0 | 2/3rds complete
Percent Compl | Original Estimate | Hours Complete
100 | 6 | 6 | = 100% Define a Json schema for IWP5.js with visualizations, examples - 6h
50 | 6 | 3 | ~ 50% Bulk convert packaged Xml Animations to their JSON counterparts, leverage php - 6h
75 | 8 | 6 | ~ 75% Choose and tool out a json schema validator application run over packaged content, refine schema - 8h
25 | 4 | 1 | ~ 25% Refactor the iwp5.js code for Animation parsing out to a new iwp5-validation.js library - 4h
Taylor
0 | 0 | 0 | - 0% Implement a circular reference detector in iwp5-validation - 8h
Albert + Niall
| 24 | 16 |  | 0.66667
December 21 is last day before break.
Providing a spreadsheet of every animation and every AUTOMATICALLY detected issue.
Next progress report : December 14th.
Milestone 1 | 1/3 Complete
100 | 2 | 2 | 100% Create Play project skeleton, CAST port - 2h
0 | 2 | 0 | 0% Provision developer laptops with new play skeleton - 2h
Albert + Taylor
50 | 4 | 2 | 50% Define Routes, Setup Layout, Welcome page - 4h Forklift as much as possible of the css / html / js from the PHP app, dont redevelop.
0 | 2 | 0 | 0% Relocate the iwp5.js content from the php folders and place over into new play location - 2h
100 | 6 | 6 | 100% Choose, Provision, and Connect to Database Tech - 6h
100 | 4 | 4 | 100% Store our first IWP animation into database from Play - 4h
25 | 8 | 2 | 25% Enable Listing + Browsing + Retrieval of Play Animations in web UI - 8h
0 | 8 | 0 | 0% Implement the Cover art capture routine, svg grabber - 8h
25 | 6 | 1.5 | 25% Bulk import of all animations and directory information to new storage - 6h
0 | 8 | 0 | 0% Production Website Cutover and Deep link preservation testing - 8h
| 50 | 17.5 |  | 0.35